## Project Plan
Phase | Scope | Task Items
Project Planning | 1.1 Create Project Timeline | 1.1.1 • Position On Timeline: 27/02/2026 • Priority: High • ID: T0001 • Category: PM • Task Name: Create Project Timeline • Description: + Complete project phases identified and structured; + Detailed task breakdown with estimated durations and dependencies; + Project timeline and Gantt chart finalized and reviewed with team. • Status: Completed • Deadline: 28/02/2026 • Assign To: Van Nam, Chu Hieu
| 1.2 Create Project Plan | 1.2.1 • Position On Timeline: 27/02/2026 • Priority: High • ID: T-02 • Category: PM • Task Name: Create Project Plan • Description: + Detailed description of all project phases based on the approved timeline; + Complex phases divided into smaller manageable units; + Final project plan document compiled, reviewed, and formatted. • Status: Completed • Deadline: 29/02/2026 • Note: Final Project Plan Derived Directly From Approved Timeline • Assign To: Xuan Phu, Minh Nguyet
| 1.3 Identify Risks And Mitigation Plan | 1.3.1 • Position On Timeline: 27/02/2026 • Priority: High • ID: T-03 • Category: PM • Task Name: Risk Identification And Mitigation Plan • Description: + Identify potential technical, schedule, and stakeholder risks affecting the project; + Define mitigation strategies and contingency actions for the identified risks; + Compile a structured Risk Management section for the project plan. • Status: Completed • Deadline: 01/03/2026 • Assign To: Minh Tien
| 1.4 Submit Plan | 1.4.1 • Position On Timeline: 01/03/2026 • Priority: High • ID: T-04 • Category: PM • Task Name: Submit Project Plan • Description: Finalize and submit the completed project plan document. Ensure all sections such as timeline, task assignments, and risk management are properly reviewed, formatted, and exported to the required format before submission. • Status: Completed • Deadline: 02/03/2026 • Assign To: Van Nam
System Design | 2.1 Design UI/UX HTML Files | 2.2.1 • Position On Timeline: 03/03/2026 • Priority: High • ID: T-05 • Category: FE • Task Name: Homepage Layout Design • Description: Design the homepage layout including navigation bar, introduction section, and system overview content. • Status: Completed • Deadline: 06/03/2026 • Assign To: Van Nam, Chu Hieu 2.2.2 • Position On Timeline: 03/03/2026 • Priority: High • ID: T-06 • Category: FE • Task Name: Homepage HTML Implementation • Description: Implement the homepage using HTML and CSS based on the designed layout. • Status: Completed • Deadline: 06/03/2026 • Assign To: Minh Nguyet, Minh Tien 2.2.3 • Position On Timeline: 07/03/2026 • Priority: High • ID: T-07 • Category: FE • Task Name: Homepage Interface Testing • Description: Test the homepage interface and ensure layout consistency across browsers. • Status: Completed • Deadline: 08/03/2026 • Assign To: Xuan Phu, Van Nam, Chu Hieu
| 2.2 Update SRS | 2.2.1 • Position On Timeline: 05/03/2026 • Priority: High • ID: T-08 • Category: Documentation • Task Name: Review Existing SRS • Description: Review the current Software Requirement Specification and identify sections that need updates or corrections based on project requirements. • Status: Completed • Deadline: 06/03/2026 • Assign To: Van Nam, Minh Tien 2.2.2 • Position On Timeline: 07/03/2026 • Priority: High • ID: T-09 • Category: Documentation • Task Name: Update SRS Content • Description: Update functional requirements, system descriptions, and use cases in the SRS document to reflect the latest project specifications. • Status: Completed • Deadline: 08/03/2026 • Assign To: Minh Nguyet 2.2.3 • Position On Timeline: 07/03/2026 • Priority: High • ID: T-10 • Category: Documentation • Task Name: Finalize Updated SRS • Description: Review and finalize the updated SRS document before moving to the system design stage. • Status: Completed • Deadline: 08/03/2026 • Assign To: Van Nam
| 2.3 Propose Design Patterns | 2.3.1 • Position On Timeline: 05/03/2026 • Priority: High • ID: T-11 • Category: Design • Task Name: Propose Design Patterns • Description: Analyze the system architecture and propose appropriate design patterns that can be used in the implementation phase to improve modularity and maintainability. • Status: Completed • Deadline: 07/03/2026 • Assign To: Xuan Phu, Chu Hieu
| 2.4 Submit Design | 2.4.1 • Position On Timeline: 07/03/2026 • Priority: High • ID: T-12 • Category: Documentation • Task Name: Submit System Design • Description: Compile and submit the final system design documentation including architecture overview and proposed design patterns. • Status: Completed • Deadline: 09/03/2026 • Assign To: Van Nam
Prototype | 3.1 Setup Project & Database | 3.1.1 • Position On Timeline: 10/03/2026 • Priority: High • ID: T-13 • Category: BE • Task Name: Setup Project Environment and Database • Description: Initialize the project repository, configure the development environment, and create the database structure required for the system including core tables. • Status: Completed • Deadline: 11/03/2026 • Assign To: Van Nam, Minh Nguyet
| 3.2 Implement Thymeleaf HTML Files | 3.2.1 • Position On Timeline: 11/03/2026 • Priority: High • ID: T-14 • Category: FE • Task Name: Implement Thymeleaf HTML Templates • Description: Implement system interface pages using Thymeleaf templates including homepage, learning pages, and navigation components. • Status: Completed • Deadline: 13/03/2026 • Assign To: Chu Hieu, Xuan Phu
| 3.3 Deliver Prototype | 3.3.1 • Position On Timeline: 14/03/2026 • Priority: High • ID: T-15 • Category: Testing • Task Name: Prototype Testing • Description: Test the prototype system to verify that implemented pages and basic system functions operate correctly before delivery. • Status: Completed • Deadline: 15/03/2026 • Assign To: Minh Tien, Minh Nguyet, Chu Hieu 3.3.2 • Position On Timeline: 15/03/2026 • Priority: High • ID: T-16 • Category: Documentation • Task Name: Deliver Prototype • Description: Deliver the prototype system and demonstrate implemented features during the project review session. • Status: Completed • Deadline: 16/03/2026 • Assign To: Minh Nguyet
Sprint 1 | 4.1 Implement Core Features | 4.1.1 • Position On Timeline: 17/03/2026 • Priority: High • ID: T-17 • Category: BE • Task Name: Course Registration Function • Description: Implement backend logic that allows users to register for available courses and store enrollment data in the database. • Status: Completed • Deadline: 20/03/2026 • Assign To: Van Nam 4.1.2 • Position On Timeline: 17/03/2026 • Priority: High • ID: T-18 • Category: FE/BE • Task Name: Course Search Feature • Description: Develop search functionality that allows users to find courses based on keywords or categories. • Status: Completed • Deadline: 20/03/2026 • Assign To: Van Nam 4.1.3 • Position On Timeline: 17/03/2026 • Priority: High • ID: T-19 • Category: FE • Task Name: Learning and Exercise Interface • Description: Develop user interface for viewing lesson materials and completing exercises. • Status: Completed • Deadline: 20/03/2026 • Assign To: Chu Hieu 4.1.4 • Position On Timeline: 17/03/2026 • Priority: High • ID: T-20 • Category: BE • Task Name: Exercise Submission and Result Tracking • Description: Implement backend logic to process exercise submissions and store user results. • Status: Completed • Deadline: 20/03/2026 • Assign To: Chu Hieu 4.1.5 • Position On Timeline: 17/03/2026 • Priority: Medium • ID: T-21 • Category: FE • Task Name: Learning Progress Display • Description: Develop interface that allows users to view their exercise scores and learning progress. • Status: Completed • Deadline: 20/03/2026 • Assign To: Chu Hieu 4.1.6 • Position On Timeline: 17/03/2026 • Priority: High • ID: T-22 • Category: FE/BE • Task Name: Change Password • Description: Implement the password management functionality according to FR-03, including both password change (while logged in) and password reset (forgot password flow). The system must provide appropriate forms, verify the user's current password, validate the strength of the new password, support email verification for password reset, encrypt the new password, and update it securely in the database. • Status: Completed • Deadline: 20/03/2026 • Assign To: Minh Nguyet 4.1.7 • Position On Timeline: 17/03/2026 • Priority: High • ID: T-23 • Category: FE/BE • Task Name: User Login Function • Description: Implement functionality allowing new users to login accounts what they created • Status: Completed • Deadline: 20/03/2026 • Assign To: Minh Nguyet 4.1.8 • Position On Timeline: 17/03/2026 • Priority: High • ID: T-24 • Category: FE/BE • Task Name: User Registration Function • Description: Implement functionality allowing users to create accounts and store their information securely. • Status: Completed • Deadline: 20/03/2026 • Assign To: Minh Nguyet 4.1.9 • Position On Timeline: 17/03/2026 • Priority: High • ID: T-25 • Category: FE/BE • Task Name: Update User Information • Description: Implement functionality allowing users to update their personal profile information. • Status: Completed • Deadline: 20/03/2026 • Assign To: Minh Tien 4.1.10 • Position On Timeline: 17/03/2026 • Priority: Medium • ID: T-26 • Category: FE/BE • Task Name: User Interaction Feature • Description: Develop system interaction features allowing users to interact with learning content or other users. • Status: Completed • Deadline: 20/03/2026 • Assign To: Minh Tien 4.1.11 • Position On Timeline: 17/03/2026 • Priority: Medium • ID: T-27 • Category: FE/BE • Task Name: Note Taking Feature • Description: Implement functionality allowing users to create and manage personal notes related to lessons. • Status: Completed • Deadline: 20/03/2026 • Assign To: Xuan Phu 4.1.12 • Position On Timeline: 17/03/2026 • Priority: Medium • ID: T-28 • Category: FE/BE • Task Name: Ranking System • Description: Build the leaderboard and badge module based on learning progress and XP/points, display top learners and the current user’s rank, and update ranking data automatically after new learning results are recorded • Status: Completed • Deadline: 20/03/2026 • Assign To: Xuan Phu 4.1.13 • Position On Timeline: 20/03/2026 • Priority: High • ID: T-29 • Category: Testing • Task Name: Functional Testing of Core Features • Description: Test core system functions including course registration, login, learning activities, and exercise submission to ensure they work correctly according to the SRS. • Status: Completed • Deadline: 21/03/2026 • Assign To: All Members 4.1.14 • Position On Timeline: 21/03/2026 • Priority: High • ID: T-30 • Category: Testing • Task Name: System Integration Testing • Description: Test the integration between frontend interfaces and backend services to verify that data flows correctly across system modules. • Status: Completed • Deadline: 22/03/2026 • Assign To: All Members 4.1.15 • Position On Timeline: 22/03/2026 • Priority: High • ID: T-31 • Category: Testing • Task Name: Bug Fixing and Verification • Description: Identify system errors during testing, fix detected issues, and verify that the corrected functions work properly. • Status: Completed • Deadline: 23/03/2026 • Assign To: All Members
| 4.2 Submit Sprint 1 | 4.2.1 • Position On Timeline: 22/03/2026 • Priority: High • ID: T-32 • Category: Documentation • Task Name: Submit Sprint 1 • Description: Compile the completed coding tasks and testing results from Sprint 1, prepare documentation, and submit the system for review. • Status: Completed • Deadline: 23/03/2026 • Assign To: Minh Nguyet
Sprint 2 | 5.1 Import Dataset | 5.1.1 • Position On Timeline: 24/03/2026 • Priority: High • ID: T-33 • Category: BE • Task Name: Prepare and Add Dataset • Description: Collect and prepare the dataset required for the system including course data, exercises, and related learning materials, then insert the dataset into the system database. • Status: Completed • Deadline: 26/03/2026 • Assign To: Minh Nguyet, Minh Tien, Chu Hieu
| 5.2 Update System Function | 5.2.1 • Position On Timeline: 26/03/2026 • Priority: Medium • ID: T-34 • Category: FE/BE • Task Name: Update System Functions • Description: Update and improve system functions based on the integrated dataset and feedback from previous sprint testing. • Status: Completed • Deadline: 29/03/2026 • Assign To: Minh Tien, Minh Nguyet, Xuan Phu
| 5.3 Submit Sprint 2 | 5.3.1 • Position On Timeline: 29/03/2026 • Priority: High • ID: T-35 • Category: Documentation • Task Name: Submit Sprint 2 • Description: Compile updated system functions, integrated dataset, and testing results completed during Sprint 2, then submit the system for review and evaluation. • Status: Completed • Deadline: 30/03/2026 • Assign To: Minh Nguyet
Sprint 3 | 6.1 Bug Fixing & Refinement | 6.1.1 • Position On Timeline: 31/03/2026 • Priority: High • ID: T-36 • Category: FE/BE • Task Name: Update System Functions • Description: Improve and refine system functionalities based on feedback from Sprint 1 and dataset integration, ensuring all learning features operate correctly. • Status: Completed • Deadline: 02/04/2026 • Assign To: All Memebers 6.1.2 • Position On Timeline: 02/04/2026 • Priority: High • ID: T-37 • Category: Testing • Task Name: System Testing • Description: Perform system testing to ensure that updated features work correctly and that all modules function properly together. • Status: Completed • Deadline: 03/04/2026 • Assign To: Xuan Phu, Minh Nguyet 6.1.3 • Position On Timeline: 03/04/2026 • Priority: High • ID: T-38 • Category: Development • Task Name: Fix System Bugs • Description: Identify and fix system bugs discovered during testing to improve system stability and performance. • Status: Completed • Deadline: 05/04/2026 • Assign To: MInh Tien, Chu Hieu, Xuan Phu 6.1.4 • Position On Timeline: 05/04/2026 • Priority: Medium • ID: T-39 • Category: Development • Task Name: Code Refactoring & Optimization • Description: Improve code quality by refactoring existing source code, optimizing system performance, and ensuring consistent coding standards across the project. • Status: Completed • Deadline: 06/04/2026 • Assign To: Minh Tien
| 6.2 Submit Sprint 3 | 6.2.1 • Position On Timeline: 04/04/2026 • Priority: High • ID: T-40 • Category: Documentation • Task Name: Submit Sprint 3 • Description: Compile the updated system after refactoring, optimization, testing, and bug fixing, then prepare documentation and submit Sprint 3 deliverables for evaluation. • Status: Completed • Deadline: 06/04/2026 • Assign To: Minh Nguyệt
Finalizing & Documentation | 7.1 Organize Repository | 7.1.1 • Position On Timeline: 06/04/2026 • Priority: High • ID: T-41 • Category: Development • Task Name: Organize Repository Structure • Description: Review and organize the project repository structure including source code, resources, configuration files, and project folders to ensure a clean and understandable structure. • Status: Pending • Deadline: 09/04/2026 • Assign To: Minh Tien
| 7.2 Client Final Approval | 7.2.1 • Position On Timeline: 09/04/2026 • Priority: High • ID: T-42 • Category: Review • Task Name: Client Final Approval • Description: Present the completed system to the client or instructor for final evaluation and approval, ensuring that all functional and non-functional requirements defined in the SRS are satisfied. • Status: Pending • Deadline: 10/04/2026 • Assign To: Minh Nguyet
Handover | 8.1 Final Handover Payment | 8.1.1 • Position On Timeline: 11/04/2026 • Priority: High • ID: T-43 • Category: PM • Task Name: Final Handover Payment Milestone • Description: Confirm completion of final handover and release of the final 20% project payment. • Status: Pending • Deadline: 12/04/2026 • Assign To: Minh Nguyet
| 8.2 Final System Handover | 8.2.1 • Position On Timeline: 12/04/2026 • Priority: High • ID: T-44 • Category: PM • Task Name: Final System Handover • Description: + Deliver the final system, repository access, and documentation to the client. + Confirm successful handover and completion of the project deliverables. • Status: Pending • Deadline: 13/04/2026 • Assign To: Minh Nguyet

## Project Timeline
|  |  |  | PHASE ONE | [6 empty] | PHASE TWO | [6 empty] | PHASE THREE | [6 empty] | PHASE FOUR | [6 empty] | PHASE FIVE | [6 empty] | PHASE SIX | [6 empty] | PHASE SEVEN | [6 empty] | PHASE EIGHT
WBS NUMBER | Scope | START DATE | DUE DATE | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11
|  |  |  | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su | M | T | W | Th | F | Sa | Su
1 | Project Planning
1.1 | Create Project Timeline | 2026-02-27 | 2026-02-28 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
1.2 | Assign Tasks | 2026-02-27 | 2026-03-01 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
1.3 | Identify Risks And Mitigation Plan | 2026-02-27 | 2026-03-01 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
1.4 | Submit Plan | 2026-03-01 | 2026-03-02 | bar: WEEK 4 F to WEEK 5 M; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
2 | System Design
2.1 | Design UI/UX HTML Files | 2026-03-03 | 2026-03-08 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 T to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
2.2 | Update SRS | 2026-03-05 | 2026-03-08 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
2.3 | Propose Design Patterns | 2026-03-05 | 2026-03-07 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
2.4 | Submit Design | 2026-03-07 | 2026-03-09 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 6 M; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
3 | Prototype
3.1 | Setup Project & Database | 2026-03-10 | 2026-03-11 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 T to WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
3.2 | Implement Thymeleaf HTML Files | 2026-03-11 | 2026-03-13 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W to WEEK 6 F; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
3.3 | Deliver Prototype | 2026-03-14 | 2026-03-16 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 6 Sa to WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
3.4 | Milestone: Prototype Approved & 20% Payment Released | 2026-03-16 | 2026-03-16 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
4 | Sprint 1
4.1 | Implement Core Features | 2026-03-17 | 2026-03-23 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
4.2 | Submit Sprint 1 | 2026-03-22 | 2026-03-23 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
5 | Sprint 2
5.1 | Import Dataset | 2026-03-24 | 2026-03-26 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
5.2 | Test Dataset | 2026-03-26 | 2026-03-29 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th to WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
5.3 | Submit Sprint 2 | 2026-03-29 | 2026-03-30 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su to WEEK 9 M; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
6 | Sprint 3
6.1 | Bug Fixing & Refinement | 2026-03-31 | 2026-04-03 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 T to WEEK 9 F; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
6.2 | Submit Sprint 3 | 2026-04-04 | 2026-04-05 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Sa to WEEK 9 Su; WEEK 10 Th to WEEK 10 F
6.3 | Milestone: Sprint 3 Completed & 20% Payment Released | 2026-04-05 | 2026-04-05 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
7 | Finalizing & Documentation
7.1 | Organize Repository | 2026-04-06 | 2026-04-09 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su to WEEK 10 F
7.2 | Client Final Approval | 2026-04-09 | 2026-04-10 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
7.2 | Milestone: Final Approval & 30% Payment Released | 2026-04-10 | 2026-04-10 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F
8 | Handover
8.1 | Milestones: Payment: 20% (Final Handover) | 2026-04-11 | 2026-04-12 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 Su
8.2 | Final System Handover | 2026-04-12 | 2026-04-13 | bar: WEEK 4 F to WEEK 4 Su; WEEK 5 Th to WEEK 5 Su; WEEK 6 W; WEEK 7 M; WEEK 7 Su to WEEK 8 M; WEEK 8 Th; WEEK 8 Su; WEEK 9 Su; WEEK 10 Th to WEEK 10 F; WEEK 10 Su to WEEK 11 M

## Risk Management Section
Risk Identification & Mitigation Strategies
Identified Risks | Description | Probability | Impact | Phase Affected | Mitigation Strategies
Stakeholder Late Payment | Stakeholder delays milestone payments, affecting project cash flow and team motivation | Medium | High | After Each Payment Milestone (Topic Approval, Prototype Approval, Sprint 3 Completion) | • Clearly define payment schedule in agreement • Pause next phase if payment is overdue • Maintain written confirmation for each milestone approval • Include late payment penalty clause
Communication Breakdown | Misunderstanding between members about requirements, task ownership, or deadlines may lead to duplicated work or missing tasks. | Medium | High | All phases | • Hold regular meetings • Maintain a shared task board • Document decisions clearly • Confirm task ownership after each meeting.
Scope Creep / Requirement Expansion | Additional features or changes are requested after the SRS and project plan have been approved, which may increase workload and delay delivery. | High | Very High | Design, Sprint 1–3, Finalizing | • Freeze the baseline scope after approval • Apply a formal change-request process • Assess impact on time and effort before accepting new changes • Prioritize only core functions first.
Integration Failure | Modules work independently but fail during integration. | Medium | High | Sprint 2–3 | • Continuous integration testing • Perform weekly integration checks
Low Technical Experience | Some members may not be familiar with the required tools, frameworks, or implementation methods, leading to slower development or more errors. | Medium | High | Design, Development, Testing | • Provide internal knowledge sharing sessions • Assign simpler tasks first • Pair less experienced members with stronger members.
Event-Driven Logic Failure for Ranking/Badge Updates | Ranking and badge features depend on correct learning-related events; if events are not generated or consumed properly, results may become inconsistent. | Medium | High | Development, Testing | • Define event rules clearly • Test event publishing/consumption thoroughly • Verify leaderboard and badge updates with sample data • Add fallback recalculation if needed.
Drop in Motivation | Long development cycles or repeated bug fixing may reduce team motivation and productivity. | Medium | Medium | Sprint 2–3, Testing | • Set short milestones recognize completed work • Rotate tasks when possible • Keep the team focused on visible progress.
Security and Access Control Issues | The system includes authentication, authorization, password handling, and logging requirements; weak security implementation may expose user data. | Medium | Very High | Development, Testing, Deployment | • Enforce server-side validation, password hashing, role-based access control, HTTPS, and secure session handling • Review sensitive endpoints carefully; test unauthorized access cases.
UI/UX Misalignment With Client Expectations | Client does not like UI after prototype despite technical correctness | Medium | High | Prototype | • Collect UI feedback before full development
Delayed Development Progress | Some tasks may take longer than planned, especially when multiple modules are being built in parallel. | Medium | High | Sprint 1–3 | • Break large tasks into smaller subtasks • Review progress weekly • Reassign work early if a task falls behind • Keep a buffer for unexpected delays.
Financial Milestones
Phase | Milestone | Financial Milestones
Proposal & Agreement | Topic Approved | 10%
Phase 6 - Prototype | Prototype Approved | 30%
Phase 9 - Sprint 3 | Sprint 3 Completed | 50%
Phase 9 - Finalizing & Documentation | Final Approval | 80%
Phase 11 - Handover & Presentation | Final Handover | 100%